## 2015 AWP covere page
UNICEF Programme of Cooperation
Work Plan
[6 empty] | Country: | Ethiopia
[6 empty] | Region: | Tigrai
National Priority: |  | Improved access to quality health, nutrition and WASH services including school WASH to the population in particular women, children and vulnerable groups through ensuring quality health service delivery through health promotion, expansion of the health extension programme, ensuring the implementation of child nutrition strategy including improving supply and distribution of iodized salt,disease prevention , curative and rehabilitative services; as well as public health emergency management and health service delivery at household, community and facility level to reduce maternal and child mortality rates, protect malaria epidemic ,and also prioritizing leadership and governance in the health sector through evidence-based policy formulation and implementation, improved planning and M&E; and the equitable and effective allocation of resources.
UNDAF Pillars and Outcome(s): |  | Pillar 2: Basic Social Service
UNDAF Outcome 6: By 2015, the Ethiopian population, in particular women, children and vulnerable groups will have improved access to and use of quality health, nutrition and WASH services
UNDAF Action Plan Output (s): |  | Output 6.1 Capacity to provide access to quality maternal and newborn health services, including family planning and PMTCT services, strengthened
UNDAP Output 6.2: Capacity to provide child and adolescent health services strengthened
UNDAP Output 6.3: National capacity for early detection and response (preventative and curative) to nutrition issues strengthened
Responsible Partner: |  |  | UNICEF
Implementing Partner(s): |  |  | Tigrai Bureau of Agriculture (BoA)
Result(s) for Agency Contribution :
No. | Agency Contribution to UNDAF Outcome(s)
By 2015, the % of girls and boys under five appropriately fed and cared for, receiving high impact nutrition interventions, and cured from malnutrition is increased
No. | Agency Contribution to UNDAF AP Output(s)
1 | Output 3: By 2015 Multi-Sectoral coordination and capacity of partners strengthened to ensure nutrition-related interventions in the household and community, with a particular focus on policy, capacity building and knowledge management
Programme Period: 2008 EFY (July 2015-June 2016) |  |  |  | Estimated annualized budget: 63,392 USD
Intervention Title: Nutrition and Food Security |  |  |  | Allocated resources:
Budget Code: _________________ |  |  |  | · Gov't | US$ | 0
Programme Component: Nutrition Multisectoral linkage |  |  |  | · Regular | RR US$ | 0
|  |  |  | ·Other: | OR US$ | 63392
Agreed by Tigrai BoPF: __________________________________________
Date | ________________________________
Agreed by MoFED: _____________________________________________
Date | ________________________________
Agreed by UNICEF:_____________________________________________
Date | ________________________________

## 2015 AWP
2015 Year Annual Work Plan (Final)
Region: Tigray - Nutrition - Multi-sectoral linkage (Tigrai Bureau of Agriculture, BoA)
UNDAF Thematic Area: UNDAF Pillar 2 Basic Social Services
Expected Results (Outcome, Outputs, indicators, baseline, annual target) | Key Intervention Areas | Activity Time Frame |  |  |  | Responsible Party | Contribution of UN agencies | Source of Fund (RR, OR, EOR…) | Budget Description | Total Amount
|  | Q1 US$ | Q2 US$ | Q3 US$ | Q4 US$
UNDAF Outcome 6 Outcome 6: By 2015, the Ethiopian population, in particular women, children and vulnerable groups will have improved access to and use of quality health, nutrition and WASH services
UNICEF Output 3: By 2015 multi sectorial coordination and capacity of partners strengthened to ensure nutrition related interventions in the HH and community with particular focuses on policy and capacity building and knowledge management (ENABLING ENVIRONMENT ) Indicator1: # of woredas with functional coordination mechanism for nutrition; Baseline: 18; Target: 31 Indicator 2. # of sector plans with integrated nutrition intervention; Baseline: 1; Target: 9
| Key Intervention Area 1.3.1 Nutrition coordination body and technical committee established at regional and woreda levels; existing coordination mechanisms at regional, woreda and kebele level strengthened; within sector TWGs established to lead the implementation of the national nutrition program in all relevant sectors at regional, zonal and woreda levels (UNDAF: Pillar 2, outcome 6 ) | [8 empty] | 0
| Activity 1.3.1.1 Conduct bi-annual regional nutrition coordination body (RNCB) and Nutrition Technical Committee (RNTC) meetings to implement NNP. |  | 720.7 |  | 720.7 | BoA, RHB & members of multisectoral linkages (NCB & NTC) | UNICEF | OR | Awareness creation, planning workshop, Review | 1441.4
| Activity 1.3.1.4 Conduct mid-year regional level review meeting to evaluate performance and strengthen Nutrition-agricultural linkages to increase access to diverse foods by households with PLW and chidlren under 2 including progress of NNP and come with recommendation for future actions | 0 | 4710.31 | 0 | 0 | BoA, RHB & members of multisectoral linkages (NCB & NTC) | UNICEF | OR | Awareness creation, planning workshop, Review | 4710.31
| Key Intervention Area 1.3.2 Establish and strengthen nutrition-agriculture linkages and improve nutrition awareness and knowledge within the agriculture/food security structure to plan nutrition sensitive agriculture interventions | [8 empty] | 0
| Activity 1.3.2.1 Conduct Training of Trainers (ToT) for 39 woreda agricultural extension experts from 13 woredas on NNP, nutrition agriculture linkages and promote nutrition sensitive agriculture interventions implementation at tabia (kebele) and household level. | 4376.18 | 0 | 0 | 0 | BoA, RHB, BoWA and WAT | UNICEF | OR | Capacity building/ training, awareness creation orientation & sensitization, and Technical Assistance | 4376.18
| Activity 1.3.2.2 Train the Agricultural Development Agents (ADA) on the importance of dietary diversity for children under two years & pregnant & lactating mothers in 13 CBN woredas (except for the Western zone). |  | 19024.81 | 28111.3 | 0 | BoA, RHB, BoWA and WAT | UNICEF | OR | Capacity building/training, awareness creation orientation & sensitization, and Technical Assistance | 47136.11
| Activity 1.3.2.7 Conduct quarterly monitoring and supportive supervision by BoA to strengthen nutrition agricultural linkages & increase access to diverse foods by households specially with PLW and children under two. | 1432 | 1432 | 1432 | 1432 | BoA, RHB, BoWA and WAT | UNICEF | OR | Capacity building/training, awareness creation orientation & sensitization, and Technical Assistance | 5728
| Total - OR | 5808.18 | 25887.82 | 29543.3 | 2152.7 |  |  |  |  | 63392

## 2015 AWP supply
Annex 6: SUPPLY PLAN FOR AWP - Nutrition Multisectoral linkages
Programme | NFS (Nutrition) |  | Region | Tigray |  | Duration/EFY | July 2015-June 2016 (2008 EFY)
Description | Unit | Unit price in USD | Qty | Total price in USD | Procurement by | Category | % Duty | Total Duty | Remark
| Each |  |  | 0 |  |  |  | 0
| Each |  |  | 0 |  |  |  | 0
| Each |  |  | 0 |  |  |  | 0
| Each |  |  | 0 |  |  |  | 0
| Each |  |  | 0 |  |  |  | 0
0

## Microplan for 2015 AWP
Nutrition-Multisectoral Linkages (BoA) 2015 AWP Detail micro-plan
S/N | Activity description | # of participants | Days | Rate | Total | Grand total | Quarter distribution
1 | Training of Trainers (ToT) for nutrition experts from 13 Woredas
| Perdiem for nutrition experts from 13 Woredas (Three from each Woreda) | 39 | 6 | 210 | 49140
| Transportation cost for 39 experts from Woreda | 39 | 2 | 100 | 7800
| Refreshment (tea/coffee/milk & sncak, mineral water & hall rent) | 45 | 4 | 100 | 18000
| Stationeries (writing pad, pen, flipchart & marker) | 45 | 1 | 40 | 1800
| Perdiem for facilitators from BoARD & BoH including 2 drivers | 8 | 6 | 210 | 10080
| Perdiem for finance & accountant including one driver | 3 | 3 | 210 | 1890
| Fuel for facilitators (BoARD) | 1 | 1 | 1400 | 1400
|  |  |  | Total-Birr | 90110 | 90110 | Q1
|  |  |  | USD | 4376.1838 | 4376.1838
2 | Training of ADA on the importance of dietary diversity for children under U2 & PLW -
| Perdium | 922 | 4 | 210 | 774480
| Stationeries (writing pad, pen, flipchart & marker) | 922 | 1 | 20 | 18440
| Refreshment (tea/coffee/milk & sncak, mineral water & hall rent) | 922 | 2 | 70 | 129080
| Transportation cost | 922 | 1 | 40 | 36880
| Facilitators cost | 39 | 3 | 100 | 11700
|  |  |  | Total-Birr | 970580 | 391600.61 | Q2
|  |  |  | USD | 47136.1274 | 578979.39 | Q3
| Training of ADA - woreda distribution | # of DA | Ratio | Share | Total
| Erob | 26 | 0.0282 |  | 27369.9349 |  | Q2
| Tahtay Adiabo | 64 | 0.069414 |  | 67372.1475 |  | Q3
| Laelay Adiabo | 84 | 0.091106 |  | 88425.9436 |  | Q2
| Tselemti | 69 | 0.074837 |  | 72635.5965 |  | Q3
| Werielehe | 98 | 0.10629 |  | 103163.6009 |  | Q2
| Gulomekeda | 63 | 0.06833 |  | 66319.4577 |  | Q3
| Hintalo Wajirat | 85 | 0.092191 |  | 89478.6334 |  | Q3
| Raya Alamata | 52 | 0.056399 |  | 54739.8698 |  | Q3
| Asgede Tsembla | 85 | 0.092191 |  | 89478.6334 |  | Q2
| Medebay Zana | 60 | 0.065076 |  | 63161.3883 |  | Q3
| Naeder Adiet | 73 | 0.079176 |  | 76846.3557 |  | Q3
| Saesi Tseda Emba | 84 | 0.091106 |  | 88425.9436 |  | Q3
| Ofla | 79 | 0.085683 |  | 83162.4946 |  | Q2
|  | 922 | 1
|  |  |  | Birr | 970580 | 970580
|  |  |  | USD | 47136.1274 | 47136.1274
3 | Mid-year Review Meeting for Nutrition FP from 34 Woredas | # of participants | Days | Rate | Total
| Perdiem for nutrition experts from 31 Woredas | 62 | 4 | 210 | 52080
| Transportation cost for Woreda experts | 62 | 2 | 100 | 12400
| Refreshment (tea/coffee/milk & sncak, mineral water & hall rent) | 75 | 2 | 100 | 15000
| Stationeries (writing pad, pen, flipchart & marker) | 75 | 1 | 30 | 2250
| Perdiem for facilitators form BoARD & BoH including two drivers | 8 | 6 | 210 | 10080
| Perdiem for finance & accountant including one driver | 3 | 6 | 210 | 3780
| Fuel for facilitators (BoARD) | 1 | 1 | 1400 | 1400
|  |  |  | Birr | 96990 | 96990 | Q2
|  |  |  | USD | 4710.3103 | 4710.3103
4 | Conduct quarterly monitoring and supportive supervision by BoA to strengthen nutrition agricultural linkages & increase access to diverse foods by households | # of participants | Days | Rate | Total
| Perdiem to monitor nutrition-agriculture linkages progress in Woredas (5 days/quarter) | 3 | 20 | 210 | 12600
| Perdiem for drivers | 1 | 20 | 210 | 4200
| Fuel cost | 1 | 20 | 600 | 12000
| Stationeries and photo copies and printing costs | 1 | 1 | 686.5 | 686.5
|  |  |  | Birr | 29486.5 | 117946 | Quarterly
|  |  |  | USD | 1432.0091 | 5728.0365
5 | Conduct bi-annual regional nutrition coordination body (RNCB) and Nutrition Technical Committee (RNTC) meetings to implement NNP
| Perdium | 40 | 1 | 210 | 8400
| Refreshment | 40 | 1 | 135 | 5400
| Stationeries and photo copies and printing costs | 40 | 1 | 25.95 | 1038
|  |  |  | Total Birr | 14838 | 29678.67 | Q2 & Q4
|  |  |  | USD | 720.7358 | 1441.4715
[5 empty] | Total expenditure | 1305304.67
[5 empty] | Budget Allocated | 1305304.672